## Gantt Chart
GANTT CHART SOLAR CELL POSITION DETECTOR
PROJECT TITLE |  | SOLAR CELL POSITION DETECTOR |  |  |  |  | COMPANY NAME | [6 empty] | Thai-Nichi Institute of Technology
PROJECT MANAGER |  | Chanaradee Prasansong |  |  |  |  | DATE | [6 empty] | 2025-01-17 | [16 empty] | Plan Time
PROJECT MEMBER |  | Pruet Phosri ¦¦ Thanakorn Techaphalangrak ¦¦ Traipop Kitipichedson ¦¦ Chanaradee Prasansong ¦¦ Ukrit Suthanawat | [28 empty] | Actual Time
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6
[7 empty] | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 30 | 31 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Meeting
1.1 | Meeting Deadline Plan | Preaw C. | 2025-01-17 | 2025-01-17 | 0 | 100% | bar: WEEK 1 17 F
1.2 | Meeting Requiment | Preaw C. | 2025-01-20 | 2025-01-20 | 0 | 0% | bar: WEEK 2 20 M
1.3 | Meeting Data Set | Preaw C. | 2025-01-21 | 2025-01-21 | 0 | 0% | bar: WEEK 2 21 T
1.4 | Meeting Deep Learning Label Plan | Preaw C. | 2025-01-22 | 2025-01-22 | 0 | 0% | bar: WEEK 2 22 W
1.5 | Meeting Deep Learning Model Plan | Preaw C. | 2025-01-23 | 2025-01-23 | 0 | 0% | bar: WEEK 2 23 R
2 | Deep Learning
2.1 | Check Requiment |  | 2025-01-20 | 2025-01-22 | 2 | 15% | bar: WEEK 2 20 M to WEEK 2 22 W
2.2 | Find Data |  | 2025-01-21 | 2025-01-24 | 3 | 0% | bar: WEEK 2 21 T to WEEK 2 24 F
2.3 | Create Layers |  | 2025-01-24 | 2025-01-27 | 3 | 0% | bar: WEEK 2 24 F to WEEK 3 27 M
2.4 | Train Model |  | 2025-01-27 | 2025-01-29 | 2 | 0% | bar: WEEK 3 27 M to WEEK 3 29 W
2.5 | Validate Model |  | 2025-01-29 | 2025-01-31 | 2 | 0% | bar: WEEK 3 28 T to WEEK 3 30 R
3 | Hard Ware
3.1 | Check Requiment | EUFA P. | 2025-01-20 | 2025-01-22 | 2 | 20% | bar: WEEK 2 20 M to WEEK 2 22 W
3.2 | Find Equipment | EUFA P. | 2025-01-21 | 2025-01-23 | 2 | 0% | bar: WEEK 2 21 T to WEEK 2 23 R
3.1 | Prepare Equipment | EUFA P. | 2025-01-23 | 2025-01-24 | 1 | 0% | bar: WEEK 2 23 R to WEEK 2 24 F
3.4 | Coding RTOS | EUFA P. | 2025-02-24 | 2025-02-27 | 3 | 0% | bar: WEEK 2 24 F to WEEK 3 29 W
3.5 | Deploy Model to Raspberry Pi | EUFA P. | 2025-01-31 | 2025-02-04 | 4 | 0% | bar: WEEK 3 30 R to WEEK 4 4 T
3.6 | Coding Servo Motor | EUFA P. | 2025-02-04 | 2025-02-07 | 3 | 0% | bar: WEEK 4 4 T to WEEK 4 7 F
3.7 | Validate Project | EUFA P. | 2025-02-07 | 2025-02-10 | 3 | 0% | bar: WEEK 4 7 F to WEEK 5 10 M
4 | Node Red
4.1 |  |  | 2025-01-17 | 2025-01-17 | 0 | 0%
4.2 |  |  | 2018-03-15 | 2018-03-16 | 1 | 0%
4.3 |  |  | 2018-03-15 | 2018-03-21 | 6 | 0%